## Q1 Operational Risks 2021-2022
UTHUKELA DISTRICT MUNICIPALITY - OPERATIONAL RISKS 2021/2022
[7 empty] | INHERENT RISK RATING (Prior to control measures put in place) |  |  |  |  | INHERENT RISK NAME | Existing Risk | CONTROL RATING | RESIDUAL RISK RATING (After control measures are put in place) |  | CONTROL NAME | RESIDUAL RISK RATING (IR) | RESIDUAL RISK NAME
Risk No | Risk Reference | Risk Category | OBJECTIVE | RISK DESCRIPTION | CAUSES OF RISK | CONSEQUENCE | IMPACT (II) |  | L/HOOD (IL) |  | RATING (IR) |  | Mitigation / Current Controls |  | IMPACT (II) | Control Rating |  |  |  | Risk Mitigation Action Plan | Risk Owner | Risk Owner | Action Owner | Start Date | Due Date | Progress on Action Plan | Progress on Action Plan | Risk Management Comments | Internal Audit Comments
Operational Risk Register 2021-2022
OR/1 | Water, Sanitation & Technical Services |  |  | Failure to account for high water losses | 1)Unmetered household. 2)Faulty meters 3)Lack of bulk meters at water treatment works to measure water leaving the plants 4)Lack of water tanker controls that is schedule of water tankers. | 1)failure to regulate indigent water usage 2)Failure to identify where water losses are incured 3)Adverse audit findings caused by abonormal high water losses | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Replacement of AC pipes in Wembezi 2)Water conservation and demand management projects 3)Water loss awareness campaigns 4)Water meters | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Installation of bulk meters at water plants, to install at 3 water plans per quarter. 2)Reconcile tracker reports on water delivered. 3)Signing of water tankers at water plants 4)To implement water conservation & demand management projects 5)Appoint X 10 meter readers 6)Installation of meters outside gated premises to enable readings, to complete 25% of the total figure per quarter 7)Internal Audit to conduct a consulting service on: 7.1)The design of controls for distribution of water by water tankers. |  | MM | 1)GM:WS&TS 2)GM:WS&TS 3)GM:WS&TS 4)GM:WS&TS 5)CFO & GM:CS 6)GM:WS&TS 7)Manager IA & GM:WS&TS | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 6)01.07.2021 7)01.07.2021 | 1)30.06.2022 2)30.09.2021 3)30.09.2021 4)Ongoing 5)30.09.2021 6)30.06.2022 7)30.09.2021
OR/2 | Water, Sanitation & Technical Services |  |  | Inability to prevent sewer spillages | 1)Ageing infrastructure 2)Vandalism at pump stations 3)Foreign objects in the sewer systems and pump stations 4)Failure to disinfect waste water | 1)Sewer spillages 2)Tarnished image of the municipality | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Reactive and predective master plan 2)Waste water treatment works | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Conduct awareness campaigns of sewer blockages. 2)Replacement of missing manhole covers, to replace 25% of covers per quarter. |  | MM | 1)GM:WS&TS 2)GM:WS&TS | 1)01.07.2021 2)01.07.2021 | 1)Ongoing 2)30.06.2022
OR/3 | Municipal Health Services & Water Services Authority |  |  | Failure to obtain green drop certification from the department of water & sanitation | 1)Shortage of skilled personnel 2)Shortage of proper operational monitoring equipment 3)Lack of standard operating procedures 4)Unsafe sampling points 5)Non-implementation of recommendations 6)Agening infrastructure | 1)Non-compliance with green drop requirments 2)Poor quality of waste water 3)Pollution of rivers and streams 4)Loss of life (human and livestock) 5)Financial loss due to law suits 6)Failure to attain a water service certification 7)Failure to comply with Department of Water & Sanitation green drop requirements | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Draft reactive & preventative plan 2)Monthly assessments of green drop 3)Monthly inspections 4)Monthly reports to WSP 5)MOU with WSP 6)Quarterly green drop progress reports 7)Waste water abatement plan | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Finalise and implement the reactive & preventative maintenance plan with corrective actions 2)Training of officials by external consultants through skills transfer 3)Uploading of all achievables in the Iris website for monitoring purposes. |  | MM | 1)GM:MHS&WSA 2)GM:MHS&WSA 3)GM:MHS&WSA | 1)01.07.2021 2)01.07.2021 3)01.07.2021 | 1)30.09.2021 2)30.09.2021 3)31.03.2022
OR/4 | Corporate Services: Fleet Management |  |  | Inadequate management of the municipal fleet | 1)Lack of standard operating procedures 2)Lack of a fleet maintenance plan 3)Failure to implement the controls in the tracking system leading to inability to reconcile kms travelled against fuel usage and inability to monitor records and municipal log books. 4)Non-timeous updates of the log books. 5)Non-adherence to the fleet management policy by management on the allocation of vehicles without prior communication with fleet manangement unit and the submission of trip authorisation forms. 6)Poor communications between fleet management and managers. 7)Non-cashbacking of depreciation on municipal assets. 8)Competency test not conducted. 9)Poor co-operation from officials. 10)Lack of directives from senior management on departmental fleet champions. | 1)Ageing fleet before the useful life of vehicles. 2)High maintenance costs. 3)High abuse of fleet 4)Abuse of overtime 5)Financial loss 6)Compromised service delivery (community paying for free services) 7)High accident rates | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Fleet management policy 2)Asset management policy 3)Municipal workshops with machanics 4)Partnership with Caltex Garage 5)Reports to portfolio committee 6)Travel vs Fuel reconcillations 7)Trip authorisation sheet 8)Wesbank vehicle controls- service provider warranties and service records. | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Develop a standard operating procedure manual to: 1.1)Send to all the user departments for inputs. 1.2)Send to Council for approval 2)Request training from the fleet tracker system controller on: 2.1)Tracking reports 2.2)Monitoring of vehicles 2.3)Access on the tracking system 3)Installation of tracking devices on all municipal fleet. 4)Conduct driver training sessions on: 4.1)Vehicle care; 4.2)Fuel usage; 4.3)Contents of the fleet management policy and 4.4)Updating of log books 5)Develop a water tanker rotation schedule. 6)Review the fleet management policy to: 6.1)Outline competeny tests and 6.2)Health assessments 7)Conduct asset verification for all fleet to: 7.1)Cancel insurance on vehicles that are no longer in existance. 7.2)Cancel vehicle licenses on non-existant vehicles and 7.3)Vehicle tracking system. 8)Review the standby overtime policy to address the allocation of vehicles to drivers on standby. 9)Conduct K53 tests for all drivers on an annual basis. 10)Review the asset management policy to outline depreciation of vehicles in consideration of all major components. |  | MM | 1)GM:CS & Fleet Manager 2)GM:CS & Fleet Manager 3)GM:CS & Fleet Manager 4)GM:CS & Fleet Manager 5)GM:CS & Fleet Manager 6)GM:CS & Fleet Manager 7)GM:CS, CFO & Fleet Manager 8)GM:CS 9)GM:CS & Fleet Manager 10)GM:CS & CFO | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 6)01.07.2021 7)01.07.2021 8)01.07.2021 9)01.07.2021 10)01.07.2021 | 1)30.09.2021 2)30.09.2021 3)30.09.2021 4)30.09.2021 5)30.09.2021 6)30.09.2021 7)30.09.2021 8)30.09.2021 9)30.09.2021 10)30.09.2021
OR/5 | Corporate Services: HR - Recruitment & Retention |  |  | Ineffective and inefficient human resource systems and processes | 1)Inadequate record keeping system 2)Delays in updating information on records arising from: missing information from Uthukela water and stolen records by employees. 3)Poor attraction and retention of skilled staff casued by a negatie reputation of the municipality and municipal system grievances. 4)Lack of electronic human resource management system. | 1)Loss of important information 2)Labour unrest 3)High staff turn-over and failure to attract critical skills. 4)Grievance arising from non-timeous updates of long-service awards and notch increaments. 5)Failure to provide correct information timely. 6)Reputational damage. 7)Loss of critical skills and poor performance. 8)Disruption of service delivery. 9)Unfair labour practices. 10)Fraud & corruption. 11)Low staff morale | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Code of conduct 2)Departmental APPs 3)Departmental scorecards 4)Human resource polices 5)Induction workshops 6)Monthly report to Manco, Portfolio & EXCO. 7)Records management policy 8)Recuitment policy 9)Weekly work plans | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Conduct a personnel file update for all municipal employees per section: 1.1)File update for Water, Sanitation & Technical Services (30/09/2021). 1.2)File update for for Municipal Health & Water Services Authority (31/12/2021). 2)Activate the Human Resource Management module on the VIP system. 3)Training of Human Resources Personnel on the use of the VIP system. 4)Reconciliation of weekly work plans against target acheived. |  | MM | 1)GM:CS & HR Manager 2)GM:CS & HR Manager 3)GM:CS & HR Manager 4)All GM's | 1.1)0107.2021 1.2)01.10.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 | 1.1)30.09.2021 1.2)31.12.2021 2)30.06.2022 3)30.09.2021 4)30.09.2021
OR/6 | Budget & Treasury Office: Revenue Collection |  |  | Inability to improve revenue collection | 1)Failure to conduct meter reading activities caused by; - Illiterate personnel to capture meter readings, - Shortage of staff to read meters, - Faulty meters. - Meters within locked premises. 2)Reluctance to pay for consumption by communities caused by;- Estimated water consumption figures. 3)Failure to reconcile variation reports. 4)The use of flat rates caused by the lack of meters in certain townships. 5)Non-replacement of meters. 6)High vacancy rate; - Manager Revenue 7)Poor quality of meters 8)Water losses caused by ageing infrastructure. 9)False entitlement to free services by the community. 10)Disgruntlements on the quality of services provided. | 1)Failure to collect on water used. 2)Financial loss 3)Going concern 4)Loss of revenue 5)Compromised service delivery 6) | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Credit control policy 2)Debtors statement 3)Finance Portfolio Committee 4)Finance by-laws 5)Interim Finance Committee 6)Meter reading 7)Reconcilation of debtors by age analysis against control accounts. 8)Section 71 reports 9)Variation reports | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Conduct monthly reconciliation of billing against the revenue vote. 2)Appoint the Revenue Manager 3)Finalise the filling of vacant posts 4)Conduct basic training on municipal finance on: 4.1)Basic accounting 4.2)Customer care skills 4.3)Financial management system |  | MM | 1)CFO & Revenue Manager 2)CFO & GM:CS 3)CFO & GM:CS 4)CFO | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 | 1)30.09.2021 2)30.09.2021 3)30.09.2021 4)30.09.2021
OR/7 | Budget & Treasury Office: Budget Management |  |  | Unfunded budget | 1)Unfunded budget resulting from high creditor costs from Umngeni Water. 2)Unfavourable contract with Umngeni Water. 3)High overtime expenditure 4)Low collection rate 5)GMs overriding departmental budgets leading to unauthorised expenditure. | 1)Non compliance with norms; - Employee Costs, - Overtime Expenditure Costs, - Repairs and Maintenance. 2)Non-receipt of equitable share 3)Tarnished image | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Budget funding plan 2)Budget funding policy 3)Budget steering committee 4)Departmental SDBIP's 5)Munsoft Mscoa compliant 6)Section 71 reports 7)Viament policy | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Finalise the termination of Umgeni Water contract. 2)Implement the budget funding plan |  | MM | 1)CFO GM:CS & MM 2)CFO | 1)01.07.2021 2)01.07.2021 | 1)30.09.2021 2)30.09.2021
OR/8 | Municipal Health Services & Water Services Authority: Food Safety |  |  | Failure to prevent food borne diseases | 1)Insufficient food sampling equipment & other resources. 2)Inadequate cash flow to ensure; - the timeous processing of food samples by an accredited laboratory. 3)Non compliance with the recommendations by food premises. 4)Failure to conduct follow-up on recommendations caused by lack of human capacity. 5)Non-implementation of recommendations | 1)Consumption of unsafe food by the public. 2)Food borne illness 3)Loss of life 4)Repeat findings on non-compliance | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Draft reactive & preventative plan 2)Food inspection checklist 3)Foof services database 4)Health promotion & education 5)Monthly reports to porfolio committee & DOH 6)Spot fines 7)Various food safety SOP's | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Fill inn vacancies on the organogram to ensure frequent site visits. 2)Finalise the promulgation of food safety by-laws: 2.1)Follow-up with legal department on submitted by-laws (31/08/2021). 2.2)Gazzette and send to Council (31.12.2021). |  | MM | 1)GM:MHS&WSA 2)GM:MHS&WSA | 1)01.07.2021 2.1)01.07.2021 2.2)01.07.2021 | 1)30.09.2021 2.1)30.09.2021 2.2)31.12.2021
OR/9 | Corporate Services: Municipal Building |  |  | Non-refurbishment of the municipal main office | 1)Lack of building maintenance plan. 2)Lack of an emergency evacuation plan. 3)Non compliance with OHS standards arising from; - Poor structural design of building. 4)Structural defects of the building. 5)Lack of a building refurbishment plan. | 1)Collapse of the building. 2)Loss of life | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Assessement from department of labour | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Develop a building refurbishment plan 1.1)Appoint service provider to conduct an assessment and development of the plan (30.09.2021). 1.2)Implement the plan (30.09.2022) |  | MM | 1)GM:CS | 1.1)01.07.2021 1.2)01.07.2021 | 1.1)30.09.2021 1.2)30.09.2022
OR/10 | Office of The Municipal Manager: Monitoring & Evaluation |  |  | Failure to evaluate the impact of projects in the extent of service delivery | 1)Lack of staff capacity 2)Lack of standard operating procedures 3)Lack of a Monitoring and Evaluation Framework and Policy. 4)Lack of annual implementation plan 5)Unclear separation of functions between M&E and PMS. 6)Lack of monitoring and evaluation tools. 7)Non alignment of the municipal objectives with the MTEF. | 1)Failure to identify and implement high impact projects. 2)Poor performance of the municipality in not achieving its objectives. 3)Community unrest and protest for basic services. 4)Reputational damage to the municipality | 4 | 2.8 | 5 | 1.5 | 20 | CRITICAL | 1)IDP | 90 |  |  | UNSATISFACTORY | 18 | MAJOR | 1)Review the job description of all M&E officials 2)Finalise the M&E policy and framework 3)Develop M&E Assessment Tools |  | MM | 1)MM 2)M&E Manager 3)M&E Manager | 1)01.07.2021 2)01.07.2021 3)01.07.2021 | 1)30.09.2021 2)30.09.2021 3)30.09.2021
OR/11 | Water, Sanitation & Technical Services: Project Implementation |  |  | Faiilure to implement projects in a timeous manner | 1)Poor project planning in relation to; - Time allocation for SCM processes. 2)Poor performance by service providers. 3)The appointment of sub-contractors who lack capacity in relation to; - Limited cash flows, - Limited expirience or none at all. 4)Unforeseen circumstances. 5)Delays in project commencement hand over. | 1)Compromised service delivery. 2)Community unrest 3)Tarnished image of the municipality. 4)Vandalism of infrastructure assets. 5)Reduction in funding allocation. | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)IDP 2)Inception report 3)Project reports 4)Project steering committees 5)SDBIP 6)Weekly planner for bid committee | 65 |  |  | MODERATE | 16.25 | MAJOR | 1)Conduct monthly stakeholder meetings 2)Commencement of SCM processes as soon as the draft budget is appoved. | MM | MM | 1)GM:WS&TS 2)GM:WS&TS | 1)01.07.2021 2)01.07.2021 | 1)30.06.2022 2)Ongoing
OR/12 | Water, Sanitation & Technical Services: Infrastructure Maintenance |  |  | Inability to maintain infrastructure assets | 1)Lack of an Infrastructure Maintenance Plan. 2)Shortage of skilled maintenance staff. 3)Re-active approach of maintenance. 4)Poor management oversight on the implementation of operations. 5)Lack of a machanical engineer. 6)Shortage of electrical staff | 1)Ageing infrastructure 2)High overtime expenditure 3) | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Panel of contractors for maintenance. 2)Reactive and predective master plan | 65 |  |  | MODERATE | 16.25 | MAJOR | 1)Develop as Asset Maintenance Plan & Asset Maintenance Schedule to develop 2 schemes per quarter. 2)Appoint a mechanical engineer and an electrical engineer. |  | MM | 1)GM:WS&TS 2)GM:CS; GM:WS&TS and MM | 1)01.07.2021 2)01.07.2021 | 1)30.06.2022 2)30.09.2021
OR/13 | Municipal Health Services & Water Services Authority: Blue Drop Drinking Water |  |  | Failure to obtain blue drop certification from the Department of Water & Sanitation | 1)Poor planning 2)Shortage of skilled personnel 3)Shortage of operational monitoring of equipment. 4)Operational and maintenance plan not implemented. | 1)Non-compliance with blue drop requirments. 2)Poor quality of drinking water 3)Financial loss 4)litigation | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)MOU between WSP & WSA 2)Quarterly compliance reports 3)Water safety plans 4)Water treatment works assessment | 65 |  |  | MODERATE | 16.25 | MAJOR | 1)Implement the reactive and preventative water implementation plan |  | MM | 1)GM:MHS&WSA | 1)01.07.2021 | 1)30.09.2021
OR/14 | Office of The Municipal Manager: Enterprise Risk Management |  |  | Ineffective implementation of risk management to provide 2nd line of defense to Council | 1)Poor response to issues of risk by the management of the municipality. 2)Poor corporate governance and failure to effect consequence management. 3)Lack of understanding on the value of risk. 4)Non-implementaion of risk mitigation plans. 5)Departmental risk champions do not submit risk mitigation plan progress and portfilio of evidence to ERM unit. 6)Risk Committee fail to meet once a quarter. 7)Shortage of staff in the ERM unit | 1)Non-compliance with legislation 2)Non-acheivement of strategic objectives. 3)Poor performance of the municipalty | 4 | 2.8 | 5 | 1.5 | 20 | CRITICAL | 1)ERM Framework, Policy & Strategy. 2)ERM Annual Implementation plan. 3)Fraud & Corruption Policy, Strategy & Prevention Plan, Whistle Blowing Policy & Compliancce Policy. 4)Risk Management Committee 5)Support from KZN Provincial Treasury | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Risk Management Committee to meet once a quarter and meetings dates will be on the dashboard of scheduled meetings. 2)Senior Managers to nominate departmental risk champions. 3)To workshop risk champions on roles, responsibilites & functions. 4)To appoint the Enterprise Risk Manager. 5)To appoint the Compliance Officer. |  | MM | 1)Risk Committee & RO 2)GM's 3)RO 4)MM 5)MM | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 | 1)31.07.2022 2)31.07.2021 3)30.09.2021 4)30.09.2021 5)30.09.2021
OR/15 | Office of The Municipal Manager: Internal Audit |  |  | Failure to evaluate and give assurance on the effectiveness on the control environment, risk management and governance processes | 1)Non-implementation of the internal auditor's recommendations by management. 2)Capacity constraints in relation to; - Human capacity 3)Failure to develop an Internal Audit Log. 4)Non-timeous review of AFSs throughout the financial year. 5)Failure to prioritise internal audit in the submission of audit evidence. 6)High levels of other commitments by management. 7)Failure to execute the internal audit plan in a timely manner. | 1)Adverse audit outcomes. 2)Poor municipal governance. 3)Compromised service delivery. 4)Tarnished image of the municipality | 4 | 2.8 | 5 | 1.5 | 20 | CRITICAL | 1)Audit Committee 2)Internal Audit Charter 3)Risk Based Audit Plan | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Develop an internal audit log to be discussed at MANCO. 2)Develop an internal audit methodology. 3)Conduct training for MANCO on the functions of internal audit services. |  | MM | 1)Manager IA 2)Manager IA 3)Manager IA | 1)01.07.2021 2)01.07.2021 3)01.07.2021 | 1)30.09.2021 2)31.12.2021 3)30.09.2021
OR/16 | Budget & Treasury Office: Contracts Management |  |  | Ineffective contract management control processes | 1)Contract register not updated timeously. 2)Poor communications between contracts management, user departments and various stakeholders. 3)Lack of performance monitoring. 4)Poor manual records management; - Lack of a record keeping system, - Lack of a contract filling room. 5)Non-alignment contracts with the financial and project management by; - Failure to update variations made cessions on contracts. - Non compliance with the 20% provision. 6)Lack of a back-up server for contracts. | 1)Non-compliance with MFMA, supply chain management and contract management policy. 2)Misstatements in annual financial statements. 3)Compromised service delivery. 4)AG queries 5)Irregular expenditure | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)Contract management policy 2)Electronic contracts register 3)Monthly reporting to MANCO, portfolio, EXCO and Council. | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Activate the contract register module on Munsoft. 2)Procure a scanner for contract management unit to upload to the main server. 3)Conduct monthly sessions with all user departments with contracts. 4)Conduct training on the use of Munsoft contract register. |  | MM | 1)CFO 2)CFO 3)CFO 4)CFO | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 | 1)30.09.2021 2)30.09.2021 3)30.06.2022 4)30.09.2021
OR/17 | Municipal Health Services & Water Services Authority: Occupational Health & Safety |  |  | Failure to prevent the occurance of occupational health & saftey hazards | 1)Budget constraints to implement; -The appointment of in-house nurses. 2)Lack of a maintenance plan for municipal buildings. 3)Lack of an evacuation plan. 4)Non implementation of recommendation; - bird mites eradication, - refurbishment of ablution facilities. 5)Lack of medical surveillance. 6)Lack of change rooms at the all municipal buildings. 7)Lack of at depots and all plants; - change rooms - ablution facilities 8)Non procurement of standard personal protective equipment for employees. | 1)Non-compliance with occupational health & safety act. 2)High rate of injury on duty incidents. 3)Loss of life. 4)Litigation. 5)Directive of non-compliance, fines by department of labour & closure of municipal buildings. | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)Fire extinguishers 2)Incident investigation forms & rerports. 3)OHS policy 4)OHS SHE Committee 5)Panel of Doctors 6)Safety reps 7)Various Training: 7.1)Advanced First Aid 7.2)SHE skills 7.3)HIRA | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Send safety reps to the following training programmes: 1.1)Hazard identification and risk assessment; 1.2)Incident reporting; and 1.3)Advanced first aid |  | MM | 1)GM:MHS&WSA | 1)01.07.2021 | 1)30.09.2021
OR/18 | Office of The Municipal Manager: Performance Management |  |  | Ineffective implementation of performance management systems | 1)Non-alignment of IDP, SDBIP & Budget. 2)Non-alignment of performance management system information and financial system. 3)Inconsistencies between reported targets and portfolio of evidence. 4)Inconsistancies between reported targets and key performance indicators. 5)Late submission of information by departments, which lead to delays in reporting. 6)Departments working in isolation. 7)Inadequate review of performance management system information by respective departments. 8)Non-submission of portfolio of evidence. 9)Poor record keeping by user departments. | 1)Inaccurate reporting. 2)Non-compliance with performance management systems. 3)Delays in reporting process. 4)Compromised service delivery. 5)Tarnished image of the municipality. 6)Failure to meet set targets. 7)Inability to monitor and report on performance | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)IDP & SDBIP Steering Committee. 2)Organisational & Departmental Scorecards. 3)PMS policy and procedual framework. 4)PMS standard operating procedure manual | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Conduct training sessions on ethics management and integrity management |  | MM | 1)PMS Manager | 1)01.07.2021 | 1)30.09.2021
OR/19 | Water, Sanitation & Technical Services: Water Supply Interruptions |  |  | Frequent water supply interruptions | 1)High vandalism of water plants. 2)High theft of electrical panels. 3)Engergy interruptions (loadshedding). 4)Ageing infrastructure 5)Drought | 1)Reluctance by communities to pay for services. 2)Reduction in revenue collection 3)Community protest. 4)Tarnished image of the municipality. 5)Dysfunctional system due to not having water. 6)Over expenditure of maintenance budget. 7)Loss of investor confidence. | 4 | 2.8 | 5 | 1.5 | 20 | CRITICAL | 1)Spring protection and bore-hole. 2)Water shedding schedule. 3)Water tankers | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Apply for a Water-Use Licence to get water supply from Woodstock Dam. |  | MM | 1)GM:WS&TS | 1)01.07.2021 | 1)30.09.2021
OR/20 | Social Economic Services: Disaster Management |  |  | Inability to respond to disasters in a timeous manner | 1)Lack of a capacity on the local municipalities to deal with disasters. 2)Lack of uniform protective gear. 3)Lack of budget to procure; - Snow chains, - Shelters, - Relief Materials -4x4 vehicles | 1)Tarnished image of the municipality. 2)Loss of life and property. 3)Non-compliance with Disaster Management Act. 4)Distruption of infrastructure. | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Disaster management centre. 2)Disaster risk officer 3)1 x Fire truck 4)Disaster management act | 65 |  |  | MODERATE | 10.4 | MODERATE | 1)Management to consider additional controls to reduce the residual risk. |  | MM | 1)GM:SES | 1)01.07.2021 | 1)30.06.2022
OR/21 | Budget & Treasury Office: Expenditure Management |  |  | Ineffective and inefficient expenditure management | 1)Lack of cash flow resulting in non-timely payments. 2) Incomplete & lack of supporting documents submitted for payments. 3)Non-submission of statements by creditors. 4)Lack of singnage for the designated point of registry for all invoices. 5)Non co-operation by user departments on the SCM procedures. | 1)Delays in payments resulting in non-compliance with legislation MFMA and AG findings. 2)Fruitless and wasteful expenditure. 3)Going concern | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Costing of payments 2)Interim finance committee 3)SCM standard operating procedure manual 4)Supply chain management policy | 65 |  |  | MODERATE | 10.4 | MODERATE | 1)Conduct training for local SMMEs on the: 1.1)Filling of tender documents; 1.2)Requirments for payments; 1.3)Completion and submission of supplier statements 2)Workshop the SCM & Expenditure operating manual to all user departments. |  | MM | 1)CFO 2)CFO | 1)01.07.2021 2)01.07.2021 | 1)30.09.2021 2)30.09.2021
OR/22 | Corporate Services: Legal Services |  |  | Failure to provide effective legal support for the municipality | 1)Lack of understanding on legal processes. 2)Fear of prejudice to testify against fellow colleagues. 3)Unfavourable cash flows which result; - Failure to pay attorney fees. -Other legal costs. 4)Failure to timeously supply the legal department with requested documentation for litigation assessments. 5)Resultance in providing information for litigation matters. 6)Failure to vet policies resulting in gaps in the policies with legal prejudice. | 1)High litigation costs. 2)High loss of cases. 3)Increase in penalties and litigations costs becoming wasteful and fruitless expenditure. 4)Tarnished image of the municipality | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Excel case register 2)Legal standard operating procedures 3)Municipal by-laws 4)Municipal policies 5)Panel of attorneys | 65 |  |  | MODERATE | 10.4 | MODERATE | 1)Get Council approval for standard operating procedures to ensure: 1.1)Mutual understanding of legal processes; 1.2)Timely submission of legal documents; and 1.3)Timely submission of support 2)Conduct awareness sessions on legal processes and requirements for all staff. 3)Develop a Case Management System in-house through ICT |  | MM | 1)GM:CS & Legal Manager 2)GM:CS & Legal Manager 3)GM:CS, Legal Manager & ICT Manager | 1)01.07.2021 2)01.07.2021 3)01.07.2021 | 1)30.09.2021 2)Ongoing 3)30.09.2021
OR/23 | Municipal Health Services & Water Services Authority: Employee Assistance Programme |  |  | Inability to operate an effective programme of employee assistance | 1)Non filling of critical vacancies at EAP; - occupational pychologist, - occupational health nurse. 2)Non timeous implementation of recommendations; - Referral of trauma cases. 3)Reprioritization of the budget allocated to EAP programmes. 4)Failure to pay panel of doctors resulting in reluctance to service the municipality. | 1)Low staff morale 2)Increased in financial pressure 3)High absenteeism 4)Compromised service delivery | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Panel of doctors and service providers 2)Safety talks 3)Wellness event planner | 65 |  |  | MODERATE | 10.4 | MODERATE | 1)Develop and Employee Assistance Programme Policy. 2)Implement wellness programmes quarterly. |  | MM | 1)GM:MHS&WSA 2)GM:MHS&WSA | 1)01.07.2021 2)01.07.2021 | 1)31.12.2021 2)Ongoing
OR/24 | Office of The Municipal Mananger: Mayoral Support |  |  | Failure to implement public awareness for mayoral programmes | 1)Lack of resources to advance; - Technological demands, - Communications demands. 2)Poor co-operation by sector departments. 3)Late / Non- submission of programmes at the OSS meetings for coordination. 4)Non establishment of formal relationships with stakeholders such as; - Moses Kotane, - DTI, - Science & Technology, - ETDP SETA. | 1)Poor implementation of the mayoral programmes. 2)The inability to intervene on social needs of the community. | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)District Disability Forum 2)District local programmes 3)Monthly reports to portfolio 4)OSS meetings 5)Weekly reports to MANCO 6)Youth development forum | 65 |  |  | MODERATE | 10.4 | MODERATE | 1)Deliberately employ people living with disabilities in the new EPWP intake. 2)Establish formal relationships with new partners sus as: 2.1)Moses Kotane; and 2.2)ETDP SETA (POE will be formal letters with response to the organisations. |  | MM | 1)MM & Manager in the Mayoral Office 2)Manager in the Mayoral Office | 1)01.07.2021 2)01.07.2021 | 1)30.09.2021 2)30.09.2021
OR/25 | Corporate Services: Leave Management |  |  | Non-timeous update of leave management | 1)Non compliance with Leave Policy in relation to; - Prior submission of leave, - Non authorisation of leave by supervisors. 2)Lack of electronic leave system | 1)High leave balances of staff. 2)High leave provision balances on the financials. 3)Financial loss 4)Failure to take recorded leave | 4 | 2.8 | 3 | 0.9 | 12 | MODERATE | 1)Leave management policy 2)Leave books 3)Leave reconciliation submitted quarterly | 65 |  |  | MODERATE | 7.8 | MINOR | 1)Activate the leave management system module on VIP |  | MM | 1)GM:CS & HR Manager | 1)01.07.2021 | 1)30.09.2021
OR/26 | Corporate Services: Skills Development & Training |  |  | Inadequate training and development of staff | 1)Insufficient budgeting to; - Implement training programmes 2)Inadequate budget caused by non timeous identification training needs by user departments. 3)Lack of priority personal development plan. 4)Lack of co-operation from staff on submission of personal development plan. | 1)Low staff morale 2)Lack of necessary skills and competencies by staff. 3)Poor performance by employees. 4)Low productivity 5)Inadequate skilled work force. 6)Compromised service delivery. | 3 | 2.1 | 4 | 1.2 | 12 | MODERATE | 1)Skills development policy 2)Skills development programmes 3)Skills retention policy | 65 |  |  | MODERATE | 7.8 | MINOR | 1)Conduct skills audit to develop a skills audit plan 2)Identify common skills shortages and enrol management for: 2.1)Change management and report writing at management level. 2.2)Business plan development course 2.3)Roles and reponsibilites for generic management 2.4)Handling and managing organizational behaviour 2.5)How to manage effective teams and supervisory aspects 2.6)Appliction of disciplinary process and emotional intelligence. 3)Develop a skills retention plan |  | MM | 1)GM:CS & HR Manager 2)GM:CS & HR Manager 3)GM:CS & HR Manager | 1)01.07.2021 2)01.07.2021 3)01.07.2021 | 1)30.09.2021 2)30.06.2022 3)30.09.2021
OR/27 | Budget & Treasury Office: Inventory Management |  |  | Inadequate inventory management processes | 1)Non-implementation of inventory policy. 2)Non-workshopping of staff 3)Lack of standard operating procedures. 4)Lack of supervision 5)Late delivery by the suppliers. 6)Non-cooperation by line managers and non-adherence to the inventory policy by line managers. 7)Lack of consequence management | 1)Financial loss 2)Over / Under statement in AFS. 3)AG findings | 3 | 2.1 | 4 | 1.2 | 12 | MODERATE | 1)Bi-Annual stock count 2)IFC 3)Inventory module on Munsoft 4)Job cards 5)Orders based on re-order levels 6)Reconcillation of ledger & store control accounts 7)SCM control procedures | 65 |  |  | MODERATE | 7.8 | MINOR | 1)Re-introduce the usage of job cards for re-ordering inventory. |  | MM | 1)CFO & SCM Manager | 1)01.07.2021 | 1)30.09.2021
OR/28 | Social Economic Services: Call Centre |  |  | Failure to respond timeously on reported faults | 1)Poor commnications between the call centre and water services. 2)Lack of an automated call centre management system. | 1)Service delivery protest 2)Community unrest 3)Tarnished image of the municipality | 3 | 2.1 | 4 | 1.2 | 12 | MODERATE | 1)Call centre reports 2)Faults dedicated reporting facility | 65 |  |  | MODERATE | 7.8 | MINOR | 1)Budget for the implementation of the Automated Call Centre Management System. |  | MM | 1)GM:SES | 1)01.07.2021 | 1)31.12.2021
OR/29 | Municipal Health Services & Water Services Authority: Environmental Management Air Quality |  |  | Failure to prevent and monitor air quality control | 1)Lack of skilled personnel; - Air quality officer 2)Poor air quality monitoring & waste management. 3)illegal dump sites 4)illegal developments and non-environmental. 5)Ineffective compliance & monitoring | 1)Vulnerabilities to disasters such as flood, storms, droughts, food, insecurity, human health illnesses and veld fires etc. 2)Non-compliance with NEMA(107 of 1998). 3)Depletion of wet lands. 4)Adverse impact on the tourism industry. 5)Loss of potential revenue. 6)Climate change 7)Increased pollution 8)Respiratory illnesses | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Air quality management plan 2)District climate change respone plan 3)Industrial emission licences baseed on: listed activities 4)Intergrated waste management plan | 40 |  |  | GOOD | 6.4 | MINOR | 1)Management to monitor existing controls to ensure continued effectiveness. |  | MM | 1)GM:MHS&WSA | 1)01.07.2021 | 1)30.06.2022
OR/30 | Office of The Municipal Manager: Integrated Development Plan (IDP) |  |  | Inability to develop a credible integrated development plan | 1)Failure by M&E to assess the impact of projects to further identify high impact projects resulting in; - Poor project identification. 2)Non alignment of budgeting cycles between the district and the sector departments. 3)Poor IGR structures between the sector departments, districts and local governments; - Failure to implement projects identified in the IDP by sector departments. - Fiscal dumping by sector departments | 1)Failure to provide water and sanitation services. 2)Tarnished image of the municipality 3)Service delivery protest | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)IDP and stakeholder engagements 2)Water master plan | 20 |  |  | VERY GOOD | 5 | INSIGNIFICANT | 1)Conduct a study on the building of a dam to address: 1.1)Water shortages and water storage; 1.2)Municipal flooding; and 1.3Energy generation |  | MM | 1)GM:WS&TS | 1)01.07.2021 | 1)31.12.2021
OR/31 | Budget & Treasury Office: Asset Management |  |  | Failure to valuate, record and safeguard municipal assets | 1)Non alignment of the budget with the Asset Maintenance Plans. 2)Non-cashbacking of depreciation of assets. | 1)Financial loss 2)Over / Under statement in AFS. 3)AG findings 4)Over / Under coverage of insurance | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Asset maintenance plan 2)Asset reconcilliations 3)Asset steering committee 4)Asset verfications | 20 |  |  | VERY GOOD | 3.2 | INSIGNIFICANT | 1)Management to monitor existing controls to ensure continued effectiveness. |  | MM | 1)CFO | 1)01.07.2021 | 1)30.06.2022
OR/32 | Social Economic Services: Local Economic Development |  |  | Lack of uThukela LED growth | 1)Lack of business growth 2)Stagnating economic growth 3)Failure to attrack new businesses/industries | 1)Shutdown of businesses within the district 2)Low employment rate 3)Loss of potential revenue 4)Increase in crime rate 5)Increase in public protests | 4 | 2.8 | 3 | 0.9 | 12 | MODERATE | 1)Local Economic Development Strategy 2)Uthukela Economic Development Agency | 20 |  |  | VERY GOOD | 2.4 | INSIGNIFICANT | 1)Management to monitor existing controls to ensure continued effectiveness. |  | MM | 1)GM:SES | 1)01.07.2021 | 1)30.06.2022
11 | B&T/3 |  |  | Ineffective and inefficient expenditure management | 1)Lack of cash flow 2)Incomplete payments submitted for payments 3)Non-submission of statements by creditors 4)Lack of singnage for the designated point of registry for all invoices 5)Non co-operation by sector departments on the SCM procedures | 1)Delays in payments resulting in non-compliance with legislation MFMA and AG findings 2)Fruitless and wasteful expenditure 3)Going concern | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)Interim finance committee 2)Monthly creditors reconciliation 3)Standard operating procedures | 65 |  |  | MODERATE | 13 | MODERATE | 1)Expenditure management cannot treat this risk as the municipality is under provincial administration. All requisitions, orders and payments are referred to the Interim Finance Committee for approval. |  | Manager: Expenditure |  | 01.07.2020 | 30.06.2021 |  | 1)Payments are processed twice a month (15th and 30th). Upon approval by IFC based on availabity of cash . 2) All payments are processed within 30 days of receipt of an invoice unless there are queries relating to supporting documentation. 3) Eskom and Telkom payments are effect via debit order to avoid interest except for three Eskom accounts where invoices are above debit order limits. (Refer creditors payment listing submitted to IFC on a weekly bases) 4) Urgent payment are submitted to the Municipal Manager and Administrator for authorization and then ratified at the next IFC meeting. | The use of the job card has not been implemented by Water and Technical Departments. No reports has been received from fleet on vehicle costing.
12 | B&T/4 |  |  | Failure to improve the audit opinion for 2019/2020 | 1)Recurring qualification issues raised by the Auditor General during the 2017/2018 financial year not resolved during the 2018/2019 financial year. 2)New issues raised during the 2018/2019 financial year. 3)Action plans developed to address the AG findings is not addressing the root causes of the findings. 4)Progress on action plan not updated timely. 5)Lack of oversight by management. 6)Lack of consequence management. | 1)Recurring qualified audit opinion. 2)Regressed audit opinion. | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)COGTA support 2)Monthly reporting of action plan progress to all committees. | 65 |  |  | MODERATE | 13 | MODERATE | 1)To develop AG action plan with relevant root causes. 2)Monthly reporting of action plan to committees and indicating the status of achievement. |  |  |  | 01.07.2020 | 30.06.2021 |  | Audit Action Plan was developed and implementation is monitored weekly in audit war room meetings. Action Plan is also tabled in portfolio committee on a monthly basis. (Refer Finance and Budget portfolio Committee meeting Agenda 15 September 2020) | Progress on the audit action plan will be reported to posrtfolio committee, Exco and Council during September 2020. The Audit Action Plan should be updated to ensure non-recurring audit findings, which will improve the audit outcome and opinion.
13 | MHS&WSA/2 |  |  | Failure to monitor and evaluate the water services provider performance on green drop | 1)Shortage of skilled personnel 2)Shortage of proper operational monitoring equipment 3)Lack of standard operating procedures 4)Unsafe sampling points | 1)Non-compliance with green drop requirments 2)Poor quality of waste water 3)Pollution of rivers and streams 4)Loss of life (human and livestock) 5)Financial loss due to law suits | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)MOU - interdepartmental relations 2)Quarterly green drop progress reports 3)Waste wate risk abatement plan | 65 |  |  | MODERATE | 13 | MODERATE | 1)MOU between WSP & WSA 2)To complie and submit compliance reports 3)To review the Waste Water risk abatement plan |  | GM: MHS &WSA |  | 1)01.07.2020 2)01.07.2020 3)01.04.2021 | 1)30.09.2020 2)30.06.2021 3)30.06.2021 |  | 1)Memorandum has been updated for the 2020 /21 financial year and signed on the 2nd July 2020. 2) 09 Waste water treatment work were monitored during the month of October to December 2020 . 3)The waste water risk abatement plan will be reviewed in the 4th quarter . | 1)Mitigation plan achieved and completed. 2)Mitigation plan is ongoing monthly, however non-compliance should be noted and improved. 3)The review will take place in the 4th Quarter. | Progress submitted with portfolio of evidence
14 | MHS&WSA/3 |  |  | Failure to timeously monitor service providers premises for safety and compliance (including food safety) | 1)Insufficient food sampling equipment & other resources 2)Lack of accredited laboratory 3)Lack of human capacity | 1)Consumption of unsafe food by the public 2)Food borne illness 3)Loss of life | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)By-laws 2)Regular inspections 3)Regular milk sampling 4)Spot fines on non-compliance with food safety | 65 |  |  | MODERATE | 13 | MODERATE | 1)To conduct regular inspections 2)To conduct milk sampling 3)To issue spot fines on non-compliance with food safety |  | GM: MHS &WSA |  | 01.07.2020 | 30.06.2021 |  | 1 )A total of 396 food premises were inspected, 193 were satisfactory and 203 were unsatisfactory. Compliance notices were issued to unsatisfactory food premises and health education was conducted. 2)Health education was conducted to 203 food handlers. 3)No fines were issued during the months of October to December 2020. | 1)Mitigation plan is ongoing monthly, however a follow up should be done on the 203 food premises that was unsatisfactory. 3)Fines should be issued for non-compliance and for generation of income to the municipality. | Progress submitted with portfolio of evidence
15 | MM/2 |  |  | Failure to implement public awareness for mayoral programmes | 1)Lack of funds 2)Lack of resources 3)Poor co-operation by sector departments 4)Late / Non- submission of programmes at the OSS meetings for coordination. | 1)Poor implementation of the mayoral programmes. 2)The inability to intervene on social needs of the community | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)District local forums 2)Municipal programmes annual plan 3)OSS meetings | 65 |  |  | MODERATE | 13 | MODERATE | 1)Foster working relations with sector departments. 2)Develop a business plan to source funding |  | Manager:Special Programmes |  | 01.07.2020 | 30.06.2021 |  | 1)Working relations with sector department is onging. 2)No funding has been received | To ensure business plans are developed to request for funding. | Progress submitted with portfolio of evidence
16 | WSTS/4 |  |  | Inability to reduce or account for water losses | 1)Ageing infrastructure 2)illegal connections 3)Lack of planned maintenance 4)Vandalism 5)Non-payment of water services by the community. 6)Water taken by water tankers not metered 7)Non-implementation of fines | 1)Loss of revenue 2)Inability to provide water services to the community 3)AG query | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Maintenance plan 2)Water conversation and demand management programmes | 80 |  |  | INADEQUATE | 12.8 | MODERATE | 1)Implementation of the revenue water master plan |  | Manager:Project Management & Operations & Maintenance |  | 01.07.2020 | 30.06.2021 |  |  | 1)Bulk meters are not installed at all extraction point to account for water taken by water tankers. 2)The non-implementation of maintenance plan will increase water losses and wastage. 3)No progress with portfolio of evidence was submitted by the department for Q2 and Q3. | Progress submitted with portfolio of evidence
17 | SES/3 |  |  | Lack of uThukela LED growth | 1)Lack of business growth 2)Stagnating economic growth 3)Failure to attrack new businesses/industries | 1)Shutdown of businesses within the district 2)Low employment rate 3)Loss of potential revenue 4)Increase in crime rate 5)Increase in public protests | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Capacitating SMMEs on accessing funds and drafting of business plans 2)District economic forum 3)Retension and expansion of businesses | 80 |  |  | INADEQUATE | 12.8 | MODERATE | 1)Reviewing the small medium micro enterprise policy to be biased towards the youth, women, disabled citizens |  | Manager:SES |  | 01.04.2021 | 30.06.2021 |  | A Business Plan for SMME Training was drafted to unlock a grant of R95 000. The SMME Procurement Policy is located the Finance Department, UEDA is coordinating the review of LM Retention Policies across the District. District LED and Tourism Forum is functional | Without funding the risk exposure will increase if no support is offered with training for SMME. | Progress submitted with portfolio of evidence
18 | CS/2 |  |  | Ineffective and inefficient human resource systems and processes that may lead to labour unrest | 1)Inadequate record keeping system 2)Delays in updating information on records 3)Poor attraction and retention of skilled staff 4)Lack of electronic human resource system | 1)Loss of important information 2)Failure to provide correct information timely 3)Reputational damage 4)Loss of critical skills and poor performance 5)Disruption of service delivery 6)Unfair labour practices 7)Fraud and corruption 8)Low staff morale | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Human resource management policy 2)Job descriptions 3)Performance management system policy 4)Records management policy | 80 |  |  | INADEQUATE | 12.8 | MODERATE | 1)Review of the human resource policies and systems 2)Source funding to upgrade the VIP system |  | 1)01.04.2021 2)01.07.2020 |  | 1)30.06.2021 2)30.09.2020 | Manager: HR | 1)The review of HR policies will commence in the 4th quarter. 2)Sourcing funding for leave module upgrade - no budget allocated for this financial year. | 1)The review of HR policies will commence in quarter 4. | 1)The risk of manual leave system could lead to errors. | 1)The Disaster Management Framework must be reviewed and amended to the new regulations adopted on the 15 March 2020.
19 | CS/3 |  |  | Inadequate training and development of staff | 1)Insufficient budgeting 2)Poor feedback on skills audit 3)Lack of priority personal development plan 4)Lack of co-operation from staff on submission of personal development plan | 1)Low staff morale 2)Lack of necessary skills and competencies by staff 3)Poor performance by employees 4)Low productivity 5)Inadequate skilled work force 6)Compromised service delivery | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Local labour forum 2)Human resource policies 3)Skills audit 4)Training committee 5)Training policy 6)Workplace skills plan | 80 |  |  | INADEQUATE | 12.8 | MODERATE | 1)Implementation of the approved workplace skills plan |  | 01.07.2020 |  | 30.06.2020 | Manager: HR | 1)Implementation is in progress as per attached training report | 1)The workplace skills plan is currently in place for the current financial period. | To reduce unskilled employees and ensure that employees are skilled with their current designations. | 1)Currently there is no system of logging calls with reference numbers.
20 | CS/4 |  |  | Failure to safeguard records of the municipality | 1)Filling system not fully functional 2)Lack of co-operation by users 3)Insufficient resources to fully implement document management plan 4)Lack of an electronic filling system 5)Lack of back-up system | 1)Loss of information or documentation 2)Non-compliance with archives act 3)Lack of audit trial 4)Inability to provide source documents during litigations 5)Breach of promotion to access of information act | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)Archives facility 2)File plan 3)Records management file plan 4)Records management policy | 80 |  |  | INADEQUATE | 12.8 | MODERATE | 1)Conduct workshops and training on the value of records management 2)Review and enforce the records management policy |  | 1)01.07.2020 2)01.04.2021 |  | 1)30.09.2020 2)30.06.2021 | Manager: Administration | 1)Training will be conducted virtually. | 1)No workshop has been conducted due to Covid-19. 2)Review of records policy will commence in the quarter 4. | To reduce the risk of manual filing misplacing documents. | Progress verified by supporting portfolio of evidence
Operational Risk Tolerance Table
Critical | Unacceptable |  |  | Risks cannot be tolerated at their current levels, activities that bring risks must be ceased until appropriate controls to reduce risks are developed and implemented. | 9
Major | Tolerable |  |  | Level of risks must be reduced unless costs associated with controls exceed associated benefits. | 10
Moderate | Tolerable |  |  | Risks at this level will only be reduced when benefits exceed the cost of reduction. | 5
Minor | Tolerable |  |  | Risks at this level will only be reduced when benefits exceed the cost of reduction. | 5
Insignificant | Acceptable |  |  | Risks are accepted at their current levels. | 3
32
Risk Mitigation Plans Due per Quarter
Quarter 1
Quarter 2
Quarter 3
Quarter 4
Note on P8: HELP ON RATINGS: Use the guidelines tabulated in the attached Risk Matrix sheet to guide you along with the ratings. Make sure that you do these ratings after Control Measures are considered and/or put in place.
Note on AA52: Slindile Gcabashe: SDF